## district summary
[11 empty] | Details of all Development Projects | [24 empty] | Annexure: 01
Physical and Financial Progress
Monthly summary
Date 2020/11/03
No. of Projects Approved |  |  |  | Approved Allocations(Rs.Mn) |  |  |  | Number ofProjects * | [8 empty] | Allocations | [8 empty] | Physical Progress ** (No. of Projects) | [10 empty] | Beneficieries
[8 empty] | Total categorized by Sectors * | [8 empty] | Total Allocation Categorized by Sectors * | [8 empty] | A | B |  |  |  | C | D | E | F | G | Expenditure (Rs. Mn)
Constructions | Goods/service purchase | Trainings | Total | Constructions | Goods/service purchase | Trainings | Total | I | II | III | IV | V | VI | VII | VIII | IX | I | II | III | IV | V | VI | VII | VIII | IX |  | Estimates Approved & Bid Documents Prepared (B1) | Quotation / Bid called (B2) | Quotation / Bid Received (B3) | Contract Awarded (B4)
6 | 3 |  |  | 5.4 |  |  | Total: 5.4; Total categorized by Sectors * I: 6; Total categorized by Sectors * VI: 2; Total Allocation Categorized by Sectors * I: 4.4; Total Allocation Categorized by Sectors * VI: 1 |  |  | 2 | [6 empty] | 7 | 4.846 | 1702
[7 empty] | Total: 0; Total Allocation Categorized by Sectors * I: 0 |  |  |  |  | 0 | [5 empty] | 0
[7 empty] | Circular Code | Sector name | [13 empty] | ** Physical progress
[7 empty] | I | Village Roads, Culverts, Bridges, Side Drinage etc. | [13 empty] | A - Estimates are being / to be prepared/Identification Location/ Identification of needs/Call for Application
[7 empty] | II | Warehouses Facilities for Agricultural Production | [13 empty] | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared preparation of Project Reports & Estimates / Approval of the Project Reports & Estimates/Selection of Beneficiaries & Resource Person/ Call for Tender/ Evaluation of Tenders/ Awarding of Tenders/ Work program completed
[7 empty] | III | Economic Centers including Weekly Faires , Small Shops
[7 empty] | IV | Construction and renovation of Small Tanks ,Canals, Anicuts,Ponds and Agricultural Wells
[7 empty] | V | Community Drinking Water Supply Projects
[7 empty] | VI | Development/Modernization of Rural Health Centers and Providing Facilities | [13 empty] | C - For Constructions : Start construction work,40% completed, Other : placed order for goods / Start of the program
[7 empty] | VII | Providing and Developing Electricity, Water and Sanitary Facilities for Schools | [13 empty] | D - For Constructions : 60% completed Other : Received goods /instruments as per the order/ Start of the Training Program & Continuation/ Completion of Traning Program
[7 empty] | VIII | Projects for Prevention of Disasters for Human habitants from wild Animals | [13 empty] | E - For Constructions 80% completed Other : Received goods /instruments as per the order/ Money payed in full & work not completed
[7 empty] | IX | Other Physical Infrastructure Improvement Projects Which are Directly Contibuted to Rural Economic Development | [13 empty] | F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries/ Work completed & payment nor completed
G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs/ Completion of Payments & works
[7 empty] | Total categorized by Sectors * IV: Details of all Development Projects | [10 empty] | Annexure: 01
Physical and Financial Progress
Monthly summary
Date 2020/11/17
No. of Projects Approved |  |  |  | Approved Allocations(Rs.Mn) |  |  | Total categorized by Sectors * I: Number ofProjects *; Total Allocation Categorized by Sectors * I: Allocations | Physical Progress ** (No. of Projects) | [10 empty] | Beneficieries
[7 empty] | Total categorized by Sectors * I: Total categorized by Sectors *; Total Allocation Categorized by Sectors * I: Total Allocation Categorized by Sectors * | A | B |  |  |  | C | D | E | F | G | Expenditure (Rs. Mn)
Constructions | Goods/service purchase | Trainings | Total | Constructions | Goods/service purchase | Trainings | Total | I | II | III | IV | V | VI | VII | VIII | IX | I | II | III | IV | V | VI | VII | VIII | IX |  | Estimates Approved & Bid Documents Prepared (B1) | Quotation / Bid called (B2) | Quotation / Bid Received (B3) | Contract Awarded (B4)
6 | 3 |  |  | 5.4 |  |  | Total: 5.4; Total categorized by Sectors * I: 6; Total categorized by Sectors * VI: 2; Total Allocation Categorized by Sectors * I: 4.4; Total Allocation Categorized by Sectors * VI: 1 |  |  | 2 | [6 empty] | 7 | 4.846 | 1702
[7 empty] | Total: 0; Total Allocation Categorized by Sectors * I: 0 |  |  |  |  | 0 | [5 empty] | 0
[7 empty] | Circular Code | Sector name | [13 empty] | ** Physical progress
[7 empty] | I | Village Roads, Culverts, Bridges, Side Drinage etc. | [13 empty] | A - Estimates are being / to be prepared/Identification Location/ Identification of needs/Call for Application
[7 empty] | II | Warehouses Facilities for Agricultural Production | [13 empty] | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared preparation of Project Reports & Estimates / Approval of the Project Reports & Estimates/Selection of Beneficiaries & Resource Person/ Call for Tender/ Evaluation of Tenders/ Awarding of Tenders/ Work program completed
[7 empty] | III | Economic Centers including Weekly Faires , Small Shops
[7 empty] | IV | Construction and renovation of Small Tanks ,Canals, Anicuts,Ponds and Agricultural Wells
[7 empty] | V | Community Drinking Water Supply Projects
[7 empty] | VI | Development/Modernization of Rural Health Centers and Providing Facilities | [13 empty] | C - For Constructions : Start construction work,40% completed, Other : placed order for goods / Start of the program
[7 empty] | VII | Providing and Developing Electricity, Water and Sanitary Facilities for Schools | [13 empty] | D - For Constructions : 60% completed Other : Received goods /instruments as per the order/ Start of the Training Program & Continuation/ Completion of Traning Program
[7 empty] | VIII | Projects for Prevention of Disasters for Human habitants from wild Animals | [13 empty] | E - For Constructions 80% completed Other : Received goods /instruments as per the order/ Money payed in full & work not completed
[7 empty] | IX | Other Physical Infrastructure Improvement Projects Which are Directly Contibuted to Rural Economic Development | [13 empty] | F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries/ Work completed & payment nor completed
G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs/ Completion of Payments & works
[7 empty] | Total categorized by Sectors * IV: Details of all Development Projects | [10 empty] | Annexure: 01
Physical and Financial Progress
Monthly summary
Date 2020/12/02
No. of Projects Approved |  |  |  | Approved Allocations(Rs.Mn) |  |  | Total categorized by Sectors * I: Number ofProjects *; Total Allocation Categorized by Sectors * I: Allocations | Physical Progress ** (No. of Projects) | [10 empty] | Beneficieries
[7 empty] | Total categorized by Sectors * I: Total categorized by Sectors *; Total Allocation Categorized by Sectors * I: Total Allocation Categorized by Sectors * | A | B |  |  |  | C | D | E | F | G | Expenditure (Rs. Mn)
Constructions | Goods/service purchase | Trainings | Total | Constructions | Goods/service purchase | Trainings | Total | I | II | III | IV | V | VI | VII | VIII | IX | I | II | III | IV | V | VI | VII | VIII | IX |  | Estimates Approved & Bid Documents Prepared (B1) | Quotation / Bid called (B2) | Quotation / Bid Received (B3) | Contract Awarded (B4)
6 | 2 |  |  | 5.4 |  |  | Total: 8; Total categorized by Sectors * I: 6; Total categorized by Sectors * VI: 2; Total Allocation Categorized by Sectors * I: 4.4; Total Allocation Categorized by Sectors * VI: 1 |  |  | 1 | [6 empty] | 7 | 4.846 | 1702
[7 empty] | Total: 0; Total Allocation Categorized by Sectors * I: 0 |  |  |  |  | 0 | [5 empty] | 0
[7 empty] | Circular Code | Sector name | [13 empty] | ** Physical progress
[7 empty] | I | Village Roads, Culverts, Bridges, Side Drinage etc. | [13 empty] | A - Estimates are being / to be prepared/Identification Location/ Identification of needs/Call for Application
[7 empty] | II | Warehouses Facilities for Agricultural Production | [13 empty] | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared preparation of Project Reports & Estimates / Approval of the Project Reports & Estimates/Selection of Beneficiaries & Resource Person/ Call for Tender/ Evaluation of Tenders/ Awarding of Tenders/ Work program completed
[7 empty] | III | Economic Centers including Weekly Faires , Small Shops
[7 empty] | IV | Construction and renovation of Small Tanks ,Canals, Anicuts,Ponds and Agricultural Wells
[7 empty] | V | Community Drinking Water Supply Projects
[7 empty] | VI | Development/Modernization of Rural Health Centers and Providing Facilities | [13 empty] | C - For Constructions : Start construction work,40% completed, Other : placed order for goods / Start of the program
[7 empty] | VII | Providing and Developing Electricity, Water and Sanitary Facilities for Schools | [13 empty] | D - For Constructions : 60% completed Other : Received goods /instruments as per the order/ Start of the Training Program & Continuation/ Completion of Traning Program
[7 empty] | VIII | Projects for Prevention of Disasters for Human habitants from wild Animals | [13 empty] | E - For Constructions 80% completed Other : Received goods /instruments as per the order/ Money payed in full & work not completed
[7 empty] | IX | Other Physical Infrastructure Improvement Projects Which are Directly Contibuted to Rural Economic Development | [13 empty] | F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries/ Work completed & payment nor completed
G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs/ Completion of Payments & works
[7 empty] | Total categorized by Sectors * IV: Details of all Development Projects | [10 empty] | Annexure: 01
Physical and Financial Progress
Monthly summary
Date 2020/12/09
No. of Projects Approved |  |  |  | Approved Allocations(Rs.Mn) |  |  | Total categorized by Sectors * I: Number ofProjects *; Total Allocation Categorized by Sectors * I: Allocations | Physical Progress ** (No. of Projects) | [10 empty] | Beneficieries
[7 empty] | Total categorized by Sectors * I: Total categorized by Sectors *; Total Allocation Categorized by Sectors * I: Total Allocation Categorized by Sectors * | A | B |  |  |  | C | D | E | F | G | Expenditure (Rs. Mn)
Constructions | Goods/service purchase | Trainings | Total | Constructions | Goods/service purchase | Trainings | Total | I | II | III | IV | V | VI | VII | VIII | IX | I | II | III | IV | V | VI | VII | VIII | IX |  | Estimates Approved & Bid Documents Prepared (B1) | Quotation / Bid called (B2) | Quotation / Bid Received (B3) | Contract Awarded (B4)
6 | 2 |  |  | 5.4 |  |  | Total: 8; Total categorized by Sectors * I: 6; Total categorized by Sectors * VI: 2; Total Allocation Categorized by Sectors * I: 4.4; Total Allocation Categorized by Sectors * VI: 1 |  |  | 1 | [6 empty] | 7 | 4.846 | 1702
[7 empty] | Total: 0; Total Allocation Categorized by Sectors * I: 0 |  |  |  |  | 0 | [5 empty] | 0
[7 empty] | Circular Code | Sector name | [13 empty] | ** Physical progress
[7 empty] | I | Village Roads, Culverts, Bridges, Side Drinage etc. | [13 empty] | A - Estimates are being / to be prepared/Identification Location/ Identification of needs/Call for Application
[7 empty] | II | Warehouses Facilities for Agricultural Production | [13 empty] | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared preparation of Project Reports & Estimates / Approval of the Project Reports & Estimates/Selection of Beneficiaries & Resource Person/ Call for Tender/ Evaluation of Tenders/ Awarding of Tenders/ Work program completed
[7 empty] | III | Economic Centers including Weekly Faires , Small Shops
[7 empty] | IV | Construction and renovation of Small Tanks ,Canals, Anicuts,Ponds and Agricultural Wells
[7 empty] | V | Community Drinking Water Supply Projects
[7 empty] | VI | Development/Modernization of Rural Health Centers and Providing Facilities | [13 empty] | C - For Constructions : Start construction work,40% completed, Other : placed order for goods / Start of the program
[7 empty] | VII | Providing and Developing Electricity, Water and Sanitary Facilities for Schools | [13 empty] | D - For Constructions : 60% completed Other : Received goods /instruments as per the order/ Start of the Training Program & Continuation/ Completion of Traning Program
[7 empty] | VIII | Projects for Prevention of Disasters for Human habitants from wild Animals | [13 empty] | E - For Constructions 80% completed Other : Received goods /instruments as per the order/ Money payed in full & work not completed
[7 empty] | IX | Other Physical Infrastructure Improvement Projects Which are Directly Contibuted to Rural Economic Development | [13 empty] | F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries/ Work completed & payment nor completed
G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs/ Completion of Payments & works

## division summary (2)
[13 empty] | Details of all Development Projects | [24 empty] | Annexure: 02
Physical and Financial Progress
Monthly summary
District- matale | [32 empty] | Date 2020/11/03
Divisional Secretariat yatawatta
No. | Source of funds | No. of Projects Approved |  |  |  | Approved Allocations(Rs.Mn) |  |  |  | Number of Projects * | [8 empty] | Allocations | [8 empty] | Physical Progress ** (No. of Projects) | [10 empty] | Beneficieries
[10 empty] | Total categorized by Sectors * | [8 empty] | Total Allocation Categorized by Sectors * | [8 empty] | A | B |  |  |  | C | D | E | F | G | Expenditure (Rs. Mn)
|  | Constructions | Goods/service purchase | Trainings | Total | Constructions | Goods/service purchase | Trainings | Total | I | II | III | IV | V | VI | VII | VIII | IX | I | II | III | IV | V | VI | VII | VIII | IX |  | Estimates Approved & Bid Documents Prepared (B1) | Quotation / Bid called (B2) | Quotation / Bid Received (B3) | Contract Awarded (B4)
1 | Ministry of Home Affairs' Vote (155)
2 | Presidential Secretariat's Vote
3 | Sapirigamak Program - 2020
4 | Rural Infrastructure Facilities Development Program RIDP | 6 | 3 |  |  | 5.4 |  |  | Total: 5.4; Total categorized by Sectors * I: 6; Total categorized by Sectors * VI: 3; Total Allocation Categorized by Sectors * I: 4.4; Total Allocation Categorized by Sectors * VI: 1 |  |  | 2 | [6 empty] | 7 | 4.846 | 1702
5 | Allocated Provisions From Provincial Council
6 | Allocated Provisions from other line Ministries (mention each ministries)
7 | Continuous Projects -2019
Divisional Total
* Projects should be categorized for following sectors
[9 empty] | Circular Code | Sector name | [13 empty] | ** Physical progress
[9 empty] | I | Village Roads, Culverts, Bridges, Side Drinage etc. | [13 empty] | A - Estimates are being / to be prepared /Identification Location/ Identification of needs/Call for Application
[9 empty] | II | Warehouses Facilities for Agricultural Production | [13 empty] | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared preparation of Project Reports & Estimates / Approval of the Project Reports & Estimates/Selection of Beneficiaries & Resource Person/ Call for Tender/ Evaluation of Tenders/ Awarding of Tenders/ Work program completed
[9 empty] | III | Economic Centers including Weekly Faires , Small Shops
[9 empty] | IV | Construction and renovation of Small Tanks ,Canals, Anicuts,Ponds and Agricultural Wells
[9 empty] | V | Community Drinking Water Supply Projects
[9 empty] | VI | Development/Modernization of Rural Health Centers and Providing Facilities | [13 empty] | C - For Constructions : Start construction work,40% completed, Other : placed order for goods/ Start of the program
[9 empty] | VII | Providing and Developing Electricity, Water and Sanitary Facilities for Schools | [13 empty] | D - For Constructions : 60% completed Other : Received goods /instruments as per the order/ Start of the Training Program & Continuation/ Completion of Traning Program
[9 empty] | VIII | Projects for Prevention of Disasters for Human habitants from wild Animals | [13 empty] | E - For Constructions 80% completed Other : Received goods /instruments as per the orderMoney payed in full & work not completed
[9 empty] | IX | Other Physical Infrastructure Improvement Projects Which are Directly Contibuted to Rural Economic Development | [13 empty] | F - For Constructions 99% completed Other : Completed lists of goods and beneficiariesWork completed & payment nor completed
G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOsCompletion of Payments & works
[9 empty] | Total categorized by Sectors * IV: Details of all Development Projects | [10 empty] | Annexure: 02
Physical and Financial Progress
Monthly summary
District- matale | [32 empty] | Date 2020/11/17
Divisional Secretariat yatawatta
No. | Source of funds | No. of Projects Approved |  |  |  | Approved Allocations(Rs.Mn) |  |  | Total categorized by Sectors * I: Number of Projects *; Total Allocation Categorized by Sectors * I: Allocations | Physical Progress ** (No. of Projects) | [10 empty] | Beneficieries
[9 empty] | Total categorized by Sectors * I: Total categorized by Sectors *; Total Allocation Categorized by Sectors * I: Total Allocation Categorized by Sectors * | A | B |  |  |  | C | D | E | F | G | Expenditure (Rs. Mn)
|  | Constructions | Goods/service purchase | Trainings | Total | Constructions | Goods/service purchase | Trainings | Total | I | II | III | IV | V | VI | VII | VIII | IX | I | II | III | IV | V | VI | VII | VIII | IX |  | Estimates Approved & Bid Documents Prepared (B1) | Quotation / Bid called (B2) | Quotation / Bid Received (B3) | Contract Awarded (B4)
1 | Ministry of Home Affairs' Vote (155)
2 | Presidential Secretariat's Vote
3 | Sapirigamak Program - 2020
4 | Rural Infrastructure Facilities Development Program RIDP | 6 | 3 |  |  | 5.4 |  |  | Total: 5.4; Total categorized by Sectors * I: 6; Total categorized by Sectors * VI: 3; Total Allocation Categorized by Sectors * I: 4.4; Total Allocation Categorized by Sectors * VI: 1 |  |  | 2 | [6 empty] | 7 | 4.846 | 1702
5 | Allocated Provisions From Provincial Council
6 | Allocated Provisions from other line Ministries (mention each ministries)
7 | Continuous Projects -2019
Divisional Total
* Projects should be categorized for following sectors
[9 empty] | Circular Code | Sector name | [13 empty] | ** Physical progress
[9 empty] | I | Village Roads, Culverts, Bridges, Side Drinage etc. | [13 empty] | A - Estimates are being / to be prepared /Identification Location/ Identification of needs/Call for Application
[9 empty] | II | Warehouses Facilities for Agricultural Production | [13 empty] | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared preparation of Project Reports & Estimates / Approval of the Project Reports & Estimates/Selection of Beneficiaries & Resource Person/ Call for Tender/ Evaluation of Tenders/ Awarding of Tenders/ Work program completed
[9 empty] | III | Economic Centers including Weekly Faires , Small Shops
[9 empty] | IV | Construction and renovation of Small Tanks ,Canals, Anicuts,Ponds and Agricultural Wells
[9 empty] | V | Community Drinking Water Supply Projects
[9 empty] | VI | Development/Modernization of Rural Health Centers and Providing Facilities | [13 empty] | C - For Constructions : Start construction work,40% completed, Other : placed order for goods/ Start of the program
[9 empty] | VII | Providing and Developing Electricity, Water and Sanitary Facilities for Schools | [13 empty] | D - For Constructions : 60% completed Other : Received goods /instruments as per the order/ Start of the Training Program & Continuation/ Completion of Traning Program
[9 empty] | VIII | Projects for Prevention of Disasters for Human habitants from wild Animals | [13 empty] | E - For Constructions 80% completed Other : Received goods /instruments as per the orderMoney payed in full & work not completed
[9 empty] | IX | Other Physical Infrastructure Improvement Projects Which are Directly Contibuted to Rural Economic Development | [13 empty] | F - For Constructions 99% completed Other : Completed lists of goods and beneficiariesWork completed & payment nor completed
G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOsCompletion of Payments & works
[9 empty] | Total categorized by Sectors * IV: Details of all Development Projects | [10 empty] | Annexure: 02
Physical and Financial Progress
Monthly summary
District- matale | [32 empty] | Date 2020/12/02
Divisional Secretariat yatawatta
No. | Source of funds | No. of Projects Approved |  |  |  | Approved Allocations(Rs.Mn) |  |  | Total categorized by Sectors * I: Number of Projects *; Total Allocation Categorized by Sectors * I: Allocations | Physical Progress ** (No. of Projects) | [10 empty] | Beneficieries
[9 empty] | Total categorized by Sectors * I: Total categorized by Sectors *; Total Allocation Categorized by Sectors * I: Total Allocation Categorized by Sectors * | A | B |  |  |  | C | D | E | F | G | Expenditure (Rs. Mn)
|  | Constructions | Goods/service purchase | Trainings | Total | Constructions | Goods/service purchase | Trainings | Total | I | II | III | IV | V | VI | VII | VIII | IX | I | II | III | IV | V | VI | VII | VIII | IX |  | Estimates Approved & Bid Documents Prepared (B1) | Quotation / Bid called (B2) | Quotation / Bid Received (B3) | Contract Awarded (B4)
1 | Ministry of Home Affairs' Vote (155)
2 | Presidential Secretariat's Vote
3 | Sapirigamak Program - 2020
4 | Rural Infrastructure Facilities Development Program RIDP | 6 | 3 |  |  | 5.4 |  |  | Total: 5.4; Total categorized by Sectors * I: 6; Total categorized by Sectors * VI: 2; Total Allocation Categorized by Sectors * I: 4.4; Total Allocation Categorized by Sectors * VI: 1 |  |  | 1 | [6 empty] | 7 | 4.846 | 1702
5 | Allocated Provisions From Provincial Council
6 | Allocated Provisions from other line Ministries (mention each ministries)
7 | Continuous Projects -2019
Divisional Total
* Projects should be categorized for following sectors
[9 empty] | Circular Code | Sector name | [13 empty] | ** Physical progress
[9 empty] | I | Village Roads, Culverts, Bridges, Side Drinage etc. | [13 empty] | A - Estimates are being / to be prepared /Identification Location/ Identification of needs/Call for Application
[9 empty] | II | Warehouses Facilities for Agricultural Production | [13 empty] | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared preparation of Project Reports & Estimates / Approval of the Project Reports & Estimates/Selection of Beneficiaries & Resource Person/ Call for Tender/ Evaluation of Tenders/ Awarding of Tenders/ Work program completed
[9 empty] | III | Economic Centers including Weekly Faires , Small Shops
[9 empty] | IV | Construction and renovation of Small Tanks ,Canals, Anicuts,Ponds and Agricultural Wells
[9 empty] | V | Community Drinking Water Supply Projects
[9 empty] | VI | Development/Modernization of Rural Health Centers and Providing Facilities | [13 empty] | C - For Constructions : Start construction work,40% completed, Other : placed order for goods/ Start of the program
[9 empty] | VII | Providing and Developing Electricity, Water and Sanitary Facilities for Schools | [13 empty] | D - For Constructions : 60% completed Other : Received goods /instruments as per the order/ Start of the Training Program & Continuation/ Completion of Traning Program
[9 empty] | VIII | Projects for Prevention of Disasters for Human habitants from wild Animals | [13 empty] | E - For Constructions 80% completed Other : Received goods /instruments as per the orderMoney payed in full & work not completed
[9 empty] | IX | Other Physical Infrastructure Improvement Projects Which are Directly Contibuted to Rural Economic Development | [13 empty] | F - For Constructions 99% completed Other : Completed lists of goods and beneficiariesWork completed & payment nor completed
G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOsCompletion of Payments & works
[9 empty] | Total categorized by Sectors * IV: Details of all Development Projects | [10 empty] | Annexure: 02
Physical and Financial Progress
Monthly summary
District- matale | [32 empty] | Date 2020/12/09
Divisional Secretariat yatawatta
No. | Source of funds | No. of Projects Approved |  |  |  | Approved Allocations(Rs.Mn) |  |  | Total categorized by Sectors * I: Number of Projects *; Total Allocation Categorized by Sectors * I: Allocations | Physical Progress ** (No. of Projects) | [10 empty] | Beneficieries
[9 empty] | Total categorized by Sectors * I: Total categorized by Sectors *; Total Allocation Categorized by Sectors * I: Total Allocation Categorized by Sectors * | A | B |  |  |  | C | D | E | F | G | Expenditure (Rs. Mn)
|  | Constructions | Goods/service purchase | Trainings | Total | Constructions | Goods/service purchase | Trainings | Total | I | II | III | IV | V | VI | VII | VIII | IX | I | II | III | IV | V | VI | VII | VIII | IX |  | Estimates Approved & Bid Documents Prepared (B1) | Quotation / Bid called (B2) | Quotation / Bid Received (B3) | Contract Awarded (B4)
1 | Ministry of Home Affairs' Vote (155)
2 | Presidential Secretariat's Vote
3 | Sapirigamak Program - 2020
4 | Rural Infrastructure Facilities Development Program RIDP | 6 | 3 |  |  | 5.4 |  |  | Total: 5.4; Total categorized by Sectors * I: 6; Total categorized by Sectors * VI: 2; Total Allocation Categorized by Sectors * I: 4.4; Total Allocation Categorized by Sectors * VI: 1 |  |  | 1 | [6 empty] | 7 | 4.846 | 1702
5 | Allocated Provisions From Provincial Council
6 | Allocated Provisions from other line Ministries (mention each ministries)
7 | Continuous Projects -2019
Divisional Total
* Projects should be categorized for following sectors
[9 empty] | Circular Code | Sector name | [13 empty] | ** Physical progress
[9 empty] | I | Village Roads, Culverts, Bridges, Side Drinage etc. | [13 empty] | A - Estimates are being / to be prepared /Identification Location/ Identification of needs/Call for Application
[9 empty] | II | Warehouses Facilities for Agricultural Production | [13 empty] | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared preparation of Project Reports & Estimates / Approval of the Project Reports & Estimates/Selection of Beneficiaries & Resource Person/ Call for Tender/ Evaluation of Tenders/ Awarding of Tenders/ Work program completed
[9 empty] | III | Economic Centers including Weekly Faires , Small Shops
[9 empty] | IV | Construction and renovation of Small Tanks ,Canals, Anicuts,Ponds and Agricultural Wells
[9 empty] | V | Community Drinking Water Supply Projects
[9 empty] | VI | Development/Modernization of Rural Health Centers and Providing Facilities | [13 empty] | C - For Constructions : Start construction work,40% completed, Other : placed order for goods/ Start of the program
[9 empty] | VII | Providing and Developing Electricity, Water and Sanitary Facilities for Schools | [13 empty] | D - For Constructions : 60% completed Other : Received goods /instruments as per the order/ Start of the Training Program & Continuation/ Completion of Traning Program
[9 empty] | VIII | Projects for Prevention of Disasters for Human habitants from wild Animals | [13 empty] | E - For Constructions 80% completed Other : Received goods /instruments as per the orderMoney payed in full & work not completed
[9 empty] | IX | Other Physical Infrastructure Improvement Projects Which are Directly Contibuted to Rural Economic Development | [13 empty] | F - For Constructions 99% completed Other : Completed lists of goods and beneficiariesWork completed & payment nor completed
G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOsCompletion of Payments & works

## detail report (hidden)
Division wise Physical and Financial Progress as at………………………………….
Division -
No. | Source of funds | Name of the Project | GN Division | Projects | [12 empty] | Allocation | [12 empty] | ** Physical Progress (No. of Projects) | [9 empty] | Expenditure (Rs. Mn) | No. of Beneficiaries
|  |  |  | No. of Projects Approved |  |  |  | Total categorized by Sectors * | [8 empty] | Allocation Made (Rs.Mn) |  |  |  | Total Allocation Categorized by Sectors * | [8 empty] | A | B |  |  |  | C | D | E | F | G
|  |  |  | Construction | Goods / Services Purchase | training | Total | I | II | III | IV | V | VI | VII | VIII | IX | Construction | Goods / Services Purchase | training | Total | I | II | III | IV | V | VI | VII | VIII | IX |  | Estimates Approved & Bid Documents Prepared (B 1) | Quotation / Bid called (B 2) | Quotation / Bid Received (B 3) | Contract Awarded (B 4)
* Projects should be categorized for following sectors
| Circular Code | Sector name | [17 empty] | ** Physical progress
| I | Village Roads, Culverts, Bridges, Side Drinage etc. | [17 empty] | A - Estimates are being / to be prepared
| II | Warehouses Facilities for Agricultural Production | [17 empty] | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called,
| III | Economic Centers including Weekly Faires , Small Shops | [17 empty] | B-3= Quotation / Bid Received, B-4= Contract Awarded Other: Identified Institutions/
| IV | Construction and renovation of Small Tanks ,Canals, Anicuts,Ponds and Agricultural Wells | [17 empty] | CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared
| V | Community Drinking Water Supply Projects | [17 empty] | C - For Constructions : Start construction work,40% completed, Other : placed order for goods
| VI | Development/Modernization of Rural Health Centers and Providing Facilities | [17 empty] | D - For Constructions : 60% completed Other : Received goods /instruments as per the order
| VII | Providing and Developing Electricity, Water and Sanitary Facilities for Schools | [17 empty] | E - For Constructions 80% completed Other : Received goods /instruments as per the order
| VIII | Projects for Prevention of Disasters for Human habitants from wild Animals | [17 empty] | G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs
| IX | Other Physical Infrastructure Improvement Projects Which are Directly
Contibuted to Rural Economic Development

## .Detail Report
Division wise Physical and Financial Progress as a 2020/11/10 | [36 empty] | Annexure: 03
District - matale
Division - yatawatta
[5 empty] | Number of Projects | [12 empty] | Allocation | [12 empty] | ** Physical Progress (No. of Projects)
[5 empty] | No. of Projects Approved |  |  |  | Total categorized by Sectors* | [8 empty] | Allocation Made (Rs.Mn) |  |  |  | Total categorized by Sectors* | [9 empty] | B
No | Source of funds | Name of the Projects |  | GN Division | Construction | Goods / Services Purchase | Trainings | Total | I | II | III | IV | V | VI | VII | VIII | IX | Construction | Goods / Services Purchase | Trainings | Total | I | II | III | IV | V | VI | VII | VIII | IX | A | Estimates Approved & Bid Documents Prepared (B 1) | Quotation / Bid called (B 2) | Quotation / Bid Received (B 3) | Contract Awarded (B 4) | C | D | E | F | G | Expenditure (Rs. Mn) | No. of Beneficiaries
|  | Sinhala | English
1 | Ministry of Finance Economy & Policy development | තල්ගහගොඩ ප්‍රධාන පාර කොන්ක්‍රිට් කිරිම | thalgahagoda pradana para concreet kireema | තල්ගහගොඩ | 1 |  |  |  | 1 | [8 empty] | 1.4 |  |  | Total: 1.4; Total categorized by Sectors* I: 1 | [8 empty] | 1 | 1.386 | 121
2 | Ministry of Finance Economy & Policy development | ඉහලවෙල මාර්ගය සංවර්ධනය කිරිම | ihalawela margaya sanwardanaya kireema | අලුත්ගම | 1 |  |  |  | 1 | [8 empty] | 0.5 |  |  | Total: 0.5; Total categorized by Sectors* I: 1 | [8 empty] | 1 | 0.495 | 350
3 | Ministry of Finance Economy & Policy development | ගමමැද පාර සංවර්ධනය කිරිම | gama mada para sanwardanya kireema | ගම්මුල්ල | 1 |  |  |  | 1 | [8 empty] | 0.5 |  |  | Total: 0.5; Total categorized by Sectors* I: 1 | [8 empty] | 1 | 0.492 | 65
4 | Ministry of Finance Economy & Policy development | මැදියාපොල පාර කොන්ක්‍රිට් කර සංවර්ධනය කිරිම | madiyapola para concreet kara sanwardanya kireema | මැදියාපොල | 1 |  |  |  | 1 | [8 empty] | 1 | [21 empty] | 1 | 0.989 | 500 | bar: Total to Total categorized by Sectors* I
5 | Ministry of Finance Economy & Policy development | එගොඩවෙල මැද පාර කොන්ක්‍රිට්කර සංවර්ධනය කිරිම | egodawela mada para concreet kara sanwardanya kireema | ඉඩංගම | 1 |  |  |  | 1 | [8 empty] | 0.5 |  |  | Total: 0.5; Total categorized by Sectors* I: 1 | [8 empty] | 1 | 0.495 | 150
6 | Ministry of Finance Economy & Policy development | බලගොල්ලැව පාර කොටසක් සංවර්ධනය කිරිම | balagollawa para kotasak sanwardanaya kireema | මාතලාපිටිය | 1 |  |  |  | 1 | [8 empty] | 0.5 |  |  | Total: 0.5; Total categorized by Sectors* I: 1 | [8 empty] | 1 | 0.494 | 16
7 | Ministry of Finance Economy & Policy development | ළමා හා මාතෘ සායන මධ්‍යස්ථානය සංවර්ධනය කිරිම | lama mathrusayan madyasthanaya sanwardanaya kireema | ඇටිපොල |  | 1 | [7 empty] | 1 |  |  |  |  | 0.5 |  | Total: 0.5; Total categorized by Sectors* VI: 1 | [8 empty] | 1 | 0.495 | 500
8 | Ministry of Finance Economy & Policy development | ළමා හා මාතෘ සායන මධ්‍යස්ථානය සංවර්ධනය කිරිම | lama mathrusayan madyasthanaya sanwardanaya kireema | මහවෙල |  | 1 | [7 empty] | 1 |  |  |  |  | 0.25 |  | Total: 0.25; Total categorized by Sectors* VI: 1 |  | 1
9 | Ministry of Finance Economy & Policy development | ළමා හා මාතෘ සායන මධ්‍යස්ථානය සංවර්ධනය කිරිම | lama mathrusayan madyasthanaya sanwardanaya kireema | රතලවැව |  | 1 | [7 empty] | 1 |  |  |  |  | 0.25 |  | Total: 0.25; Total categorized by Sectors* VI: 1 |  | 1
Total |  |  |  |  | 6 | 3 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 4.4 | 1 | 0 | 5.4 | 6 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 4.846 | 1702
* Projects should be categorized for following sectors
|  |  | Circular Code | Sector name | [16 empty] | Total: ** Physical progress
|  |  | I | Village Roads, Culverts, Bridges, Side Drinage etc. | [16 empty] | Total: A - Estimates are being / to be prepared/Identification Location/ Identification of needs/Call for Application
|  |  | II | Warehouses Facilities for Agricultural Production | [16 empty] | Total: B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared preparation of Project Reports & Estimates / Approval of the Project Reports & Estimates/Selection of Beneficiaries & Resource Person/ Call for Tender/ Evaluation of Tenders/ Awarding of Tenders/ Work program completed
|  |  | III | Economic Centers including Weekly Faires , Small Shops
|  |  | IV | Construction and renovation of Small Tanks ,Canals, Anicuts,Ponds and Agricultural Wells
|  |  | V | Community Drinking Water Supply Projects
|  |  | VI | Development/Modernization of Rural Health Centers and Providing Facilities | [16 empty] | Total: C - For Constructions : Start construction work,40% completed, Other : placed order for goods / Start of the program
|  |  | VII | Providing and Developing Electricity, Water and Sanitary Facilities for Schools | [16 empty] | Total: D - For Constructions : 60% completed Other : Received goods /instruments as per the order/ Start of the Training Program & Continuation/ Completion of Traning Program
|  |  | VIII | Projects for Prevention of Disasters for Human habitants from wild Animals | [16 empty] | Total: E - For Constructions 80% completed Other : Received goods /instruments as per the orderMoney payed in full & work not completed
|  |  | IX | Other Physical Infrastructure Improvement Projects Which are Directly Contibuted to Rural Economic Development | [16 empty] | Total: F - For Constructions 99% completed Other : Completed lists of goods and beneficiariesWork completed & payment nor completed
G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOsCompletion of Payments & works
** THIS FORMAT SHOULD BE SENT SEPERATLY ACCORDING TO AUTHORISED AGENCY TO IMPLEMENT.
Division wise Physical and Financial Progress as a 2020/11/17 | [36 empty] | Annexure: 03
District - matale
Division - yatawatta
[5 empty] | Number of Projects | [12 empty] | Allocation |  |  | Total categorized by Sectors* A: ** Physical Progress (No. of Projects)
[5 empty] | No. of Projects Approved |  |  |  | Total categorized by Sectors* | [8 empty] | Allocation Made (Rs.Mn) |  |  | Total categorized by Sectors* I: Total categorized by Sectors* | B
No | Source of funds | Name of the Projects |  | GN Division | Construction | Goods / Services Purchase | Trainings | Total | I | II | III | IV | V | VI | VII | VIII | IX | Construction | Goods / Services Purchase | Trainings | Total | I | II | III | IV | V | VI | VII | VIII | IX | A | Estimates Approved & Bid Documents Prepared (B 1) | Quotation / Bid called (B 2) | Quotation / Bid Received (B 3) | Contract Awarded (B 4) | C | D | E | F | G | Expenditure (Rs. Mn) | No. of Beneficiaries
|  | Sinhala | English
1 | Ministry of Finance Economy & Policy development | තල්ගහගොඩ ප්‍රධාන පාර කොන්ක්‍රිට් කිරිම | thalgahagoda pradana para concreet kireema | තල්ගහගොඩ | 1 |  |  |  | 1 | [8 empty] | 1.4 |  |  | Total: 1.4; Total categorized by Sectors* I: 1 | [8 empty] | 1 | 1.386 | 121
2 | Ministry of Finance Economy & Policy development | ඉහලවෙල මාර්ගය සංවර්ධනය කිරිම | ihalawela margaya sanwardanaya kireema | අලුත්ගම | 1 |  |  |  | 1 | [8 empty] | 0.5 |  |  | Total: 0.5; Total categorized by Sectors* I: 1 | [8 empty] | 1 | 0.495 | 350
3 | Ministry of Finance Economy & Policy development | ගමමැද පාර සංවර්ධනය කිරිම | gama mada para sanwardanya kireema | ගම්මුල්ල | 1 |  |  |  | 1 | [8 empty] | 0.5 |  |  | Total: 0.5; Total categorized by Sectors* I: 1 | [8 empty] | 1 | 0.492 | 65
4 | Ministry of Finance Economy & Policy development | මැදියාපොල පාර කොන්ක්‍රිට් කර සංවර්ධනය කිරිම | madiyapola para concreet kara sanwardanya kireema | මැදියාපොල | 1 |  |  |  | 1 | [8 empty] | 1 | [21 empty] | 1 | 0.989 | 500 | bar: Total to Total categorized by Sectors* I
5 | Ministry of Finance Economy & Policy development | එගොඩවෙල මැද පාර කොන්ක්‍රිට්කර සංවර්ධනය කිරිම | egodawela mada para concreet kara sanwardanya kireema | ඉඩංගම | 1 |  |  |  | 1 | [8 empty] | 0.5 |  |  | Total: 0.5; Total categorized by Sectors* I: 1 | [8 empty] | 1 | 0.495 | 150
6 | Ministry of Finance Economy & Policy development | බලගොල්ලැව පාර කොටසක් සංවර්ධනය කිරිම | balagollawa para kotasak sanwardanaya kireema | මාතලාපිටිය | 1 |  |  |  | 1 | [8 empty] | 0.5 |  |  | Total: 0.5; Total categorized by Sectors* I: 1 | [8 empty] | 1 | 0.494 | 16
7 | Ministry of Finance Economy & Policy development | ළමා හා මාතෘ සායන මධ්‍යස්ථානය සංවර්ධනය කිරිම | lama mathrusayan madyasthanaya sanwardanaya kireema | ඇටිපොල |  | 1 | [7 empty] | 1 |  |  |  |  | 0.5 |  | Total: 0.5; Total categorized by Sectors* VI: 1 | [8 empty] | 1 | 0.495 | 500
8 | Ministry of Finance Economy & Policy development | ළමා හා මාතෘ සායන මධ්‍යස්ථානය සංවර්ධනය කිරිම | lama mathrusayan madyasthanaya sanwardanaya kireema | මහවෙල |  | 1 | [7 empty] | 1 |  |  |  |  | 0.25 |  | Total: 0.25; Total categorized by Sectors* VI: 1 |  | 1
9 | Ministry of Finance Economy & Policy development | ළමා හා මාතෘ සායන මධ්‍යස්ථානය සංවර්ධනය කිරිම | lama mathrusayan madyasthanaya sanwardanaya kireema | රතලවැව |  | 1 | [7 empty] | 1 |  |  |  |  | 0.25 |  | Total: 0.25; Total categorized by Sectors* VI: 1 |  | 1
Total |  |  |  |  | 6 | 3 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 4.4 | 1 | 0 | 5.4 | 6 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 4.846 | 1702
* Projects should be categorized for following sectors
|  |  | Circular Code | Sector name | [16 empty] | Total: ** Physical progress
|  |  | I | Village Roads, Culverts, Bridges, Side Drinage etc. | [16 empty] | Total: A - Estimates are being / to be prepared/Identification Location/ Identification of needs/Call for Application
|  |  | II | Warehouses Facilities for Agricultural Production | [16 empty] | Total: B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared preparation of Project Reports & Estimates / Approval of the Project Reports & Estimates/Selection of Beneficiaries & Resource Person/ Call for Tender/ Evaluation of Tenders/ Awarding of Tenders/ Work program completed
|  |  | III | Economic Centers including Weekly Faires , Small Shops
|  |  | IV | Construction and renovation of Small Tanks ,Canals, Anicuts,Ponds and Agricultural Wells
|  |  | V | Community Drinking Water Supply Projects
|  |  | VI | Development/Modernization of Rural Health Centers and Providing Facilities | [16 empty] | Total: C - For Constructions : Start construction work,40% completed, Other : placed order for goods / Start of the program
|  |  | VII | Providing and Developing Electricity, Water and Sanitary Facilities for Schools | [16 empty] | Total: D - For Constructions : 60% completed Other : Received goods /instruments as per the order/ Start of the Training Program & Continuation/ Completion of Traning Program
|  |  | VIII | Projects for Prevention of Disasters for Human habitants from wild Animals | [16 empty] | Total: E - For Constructions 80% completed Other : Received goods /instruments as per the orderMoney payed in full & work not completed
|  |  | IX | Other Physical Infrastructure Improvement Projects Which are Directly Contibuted to Rural Economic Development | [16 empty] | Total: F - For Constructions 99% completed Other : Completed lists of goods and beneficiariesWork completed & payment nor completed
G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOsCompletion of Payments & works
Division wise Physical and Financial Progress as a 2020/12/02 | [36 empty] | Annexure: 03
District - matale
Division - yatawatta
[5 empty] | Number of Projects | [12 empty] | Allocation |  |  | Total categorized by Sectors* A: ** Physical Progress (No. of Projects)
[5 empty] | No. of Projects Approved |  |  |  | Total categorized by Sectors* | [8 empty] | Allocation Made (Rs.Mn) |  |  | Total categorized by Sectors* I: Total categorized by Sectors* | B
No | Source of funds | Name of the Projects |  | GN Division | Construction | Goods / Services Purchase | Trainings | Total | I | II | III | IV | V | VI | VII | VIII | IX | Construction | Goods / Services Purchase | Trainings | Total | I | II | III | IV | V | VI | VII | VIII | IX | A | Estimates Approved & Bid Documents Prepared (B 1) | Quotation / Bid called (B 2) | Quotation / Bid Received (B 3) | Contract Awarded (B 4) | C | D | E | F | G
|  | Sinhala | English
1 | Ministry of Finance Economy & Policy development | තල්ගහගොඩ ප්‍රධාන පාර කොන්ක්‍රිට් කිරිම | thalgahagoda pradana para concreet kireema | තල්ගහගොඩ | 1 |  |  |  | 1 | [8 empty] | 1.4 |  |  | Total: 1.4; Total categorized by Sectors* I: 1 | [8 empty] | 1
2 | Ministry of Finance Economy & Policy development | ඉහලවෙල මාර්ගය සංවර්ධනය කිරිම | ihalawela margaya sanwardanaya kireema | අලුත්ගම | 1 |  |  |  | 1 | [8 empty] | 0.5 |  |  | Total: 0.5; Total categorized by Sectors* I: 1 | [8 empty] | 1
3 | Ministry of Finance Economy & Policy development | ගමමැද පාර සංවර්ධනය කිරිම | gama mada para sanwardanya kireema | ගම්මුල්ල | 1 |  |  |  | 1 | [8 empty] | 0.5 |  |  | Total: 0.5; Total categorized by Sectors* I: 1 | [8 empty] | 1
4 | Ministry of Finance Economy & Policy development | මැදියාපොල පාර කොන්ක්‍රිට් කර සංවර්ධනය කිරිම | madiyapola para concreet kara sanwardanya kireema | මැදියාපොල | 1 |  |  |  | 1 | [8 empty] | 1 | [21 empty] | 1 | bar: Total to Total categorized by Sectors* I
5 | Ministry of Finance Economy & Policy development | එගොඩවෙල මැද පාර කොන්ක්‍රිට්කර සංවර්ධනය කිරිම | egodawela mada para concreet kara sanwardanya kireema | ඉඩංගම | 1 |  |  |  | 1 | [8 empty] | 0.5 |  |  | Total: 0.5; Total categorized by Sectors* I: 1 | [8 empty] | 1
6 | Ministry of Finance Economy & Policy development | බලගොල්ලැව පාර කොටසක් සංවර්ධනය කිරිම | balagollawa para kotasak sanwardanaya kireema | මාතලාපිටිය | 1 |  |  |  | 1 | [8 empty] | 0.5 |  |  | Total: 0.5; Total categorized by Sectors* I: 1 | [8 empty] | 1
7 | Ministry of Finance Economy & Policy development | ළමා හා මාතෘ සායන මධ්‍යස්ථානය සංවර්ධනය කිරිම | lama mathrusayan madyasthanaya sanwardanaya kireema | ඇටිපොල |  | 1 | [7 empty] | 1 |  |  |  |  | 0.5 |  | Total: 0.5; Total categorized by Sectors* VI: 1 | [8 empty] | 1
8 | Ministry of Finance Economy & Policy development | ළමා හා මාතෘ සායන මධ්‍යස්ථානය සංවර්ධනය කිරිම | lama mathrusayan madyasthanaya sanwardanaya kireema | මහවෙල |  | 1 | [7 empty] | 1 |  |  |  |  | 0.5 |  | Total: 0.5; Total categorized by Sectors* VI: 1 |  | 1
Total |  |  |  |  | 6 | 2 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 4.4 | 1 | 0 | 5.4 | 6 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 7
* Projects should be categorized for following sectors
|  |  | Circular Code | Sector name | [16 empty] | Total: ** Physical progress
|  |  | I | Village Roads, Culverts, Bridges, Side Drinage etc. | [16 empty] | Total: A - Estimates are being / to be prepared/Identification Location/ Identification of needs/Call for Application
|  |  | II | Warehouses Facilities for Agricultural Production | [16 empty] | Total: B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared preparation of Project Reports & Estimates / Approval of the Project Reports & Estimates/Selection of Beneficiaries & Resource Person/ Call for Tender/ Evaluation of Tenders/ Awarding of Tenders/ Work program completed
|  |  | III | Economic Centers including Weekly Faires , Small Shops
|  |  | IV | Construction and renovation of Small Tanks ,Canals, Anicuts,Ponds and Agricultural Wells
|  |  | V | Community Drinking Water Supply Projects
|  |  | VI | Development/Modernization of Rural Health Centers and Providing Facilities | [16 empty] | Total: C - For Constructions : Start construction work,40% completed, Other : placed order for goods / Start of the program
|  |  | VII | Providing and Developing Electricity, Water and Sanitary Facilities for Schools | [16 empty] | Total: D - For Constructions : 60% completed Other : Received goods /instruments as per the order/ Start of the Training Program & Continuation/ Completion of Traning Program
|  |  | VIII | Projects for Prevention of Disasters for Human habitants from wild Animals | [16 empty] | Total: E - For Constructions 80% completed Other : Received goods /instruments as per the orderMoney payed in full & work not completed
|  |  | IX | Other Physical Infrastructure Improvement Projects Which are Directly Contibuted to Rural Economic Development | [16 empty] | Total: F - For Constructions 99% completed Other : Completed lists of goods and beneficiariesWork completed & payment nor completed
G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOsCompletion of Payments & works
Division wise Physical and Financial Progress as a 2020/12/09 | [36 empty] | Annexure: 03
District - matale
Division - yatawatta
[5 empty] | Number of Projects | [12 empty] | Allocation |  |  | Total categorized by Sectors* A: ** Physical Progress (No. of Projects)
[5 empty] | No. of Projects Approved |  |  |  | Total categorized by Sectors* | [8 empty] | Allocation Made (Rs.Mn) |  |  | Total categorized by Sectors* I: Total categorized by Sectors* | B
No | Source of funds | Name of the Projects |  | GN Division | Construction | Goods / Services Purchase | Trainings | Total | I | II | III | IV | V | VI | VII | VIII | IX | Construction | Goods / Services Purchase | Trainings | Total | I | II | III | IV | V | VI | VII | VIII | IX | A | Estimates Approved & Bid Documents Prepared (B 1) | Quotation / Bid called (B 2) | Quotation / Bid Received (B 3) | Contract Awarded (B 4) | C | D | E | F | G
|  | Sinhala | English
1 | Ministry of Finance Economy & Policy development | තල්ගහගොඩ ප්‍රධාන පාර කොන්ක්‍රිට් කිරිම | thalgahagoda pradana para concreet kireema | තල්ගහගොඩ | 1 |  |  |  | 1 | [8 empty] | 1.4 |  |  | Total: 1.4; Total categorized by Sectors* I: 1 | [8 empty] | 1
2 | Ministry of Finance Economy & Policy development | ඉහලවෙල මාර්ගය සංවර්ධනය කිරිම | ihalawela margaya sanwardanaya kireema | අලුත්ගම | 1 |  |  |  | 1 | [8 empty] | 0.5 |  |  | Total: 0.5; Total categorized by Sectors* I: 1 | [8 empty] | 1
3 | Ministry of Finance Economy & Policy development | ගමමැද පාර සංවර්ධනය කිරිම | gama mada para sanwardanya kireema | ගම්මුල්ල | 1 |  |  |  | 1 | [8 empty] | 0.5 |  |  | Total: 0.5; Total categorized by Sectors* I: 1 | [8 empty] | 1
4 | Ministry of Finance Economy & Policy development | මැදියාපොල පාර කොන්ක්‍රිට් කර සංවර්ධනය කිරිම | madiyapola para concreet kara sanwardanya kireema | මැදියාපොල | 1 |  |  |  | 1 | [8 empty] | 1 | [21 empty] | 1 | bar: Total to Total categorized by Sectors* I
5 | Ministry of Finance Economy & Policy development | එගොඩවෙල මැද පාර කොන්ක්‍රිට්කර සංවර්ධනය කිරිම | egodawela mada para concreet kara sanwardanya kireema | ඉඩංගම | 1 |  |  |  | 1 | [8 empty] | 0.5 |  |  | Total: 0.5; Total categorized by Sectors* I: 1 | [8 empty] | 1
6 | Ministry of Finance Economy & Policy development | බලගොල්ලැව පාර කොටසක් සංවර්ධනය කිරිම | balagollawa para kotasak sanwardanaya kireema | මාතලාපිටිය | 1 |  |  |  | 1 | [8 empty] | 0.5 |  |  | Total: 0.5; Total categorized by Sectors* I: 1 | [8 empty] | 1
7 | Ministry of Finance Economy & Policy development | ළමා හා මාතෘ සායන මධ්‍යස්ථානය සංවර්ධනය කිරිම | lama mathrusayan madyasthanaya sanwardanaya kireema | ඇටිපොල |  | 1 | [7 empty] | 1 |  |  |  |  | 0.5 |  | Total: 0.5; Total categorized by Sectors* VI: 1 | [8 empty] | 1
8 | Ministry of Finance Economy & Policy development | ළමා හා මාතෘ සායන මධ්‍යස්ථානය සංවර්ධනය කිරිම | lama mathrusayan madyasthanaya sanwardanaya kireema | මහවෙල |  | 1 | [7 empty] | 1 |  |  |  |  | 0.5 |  | Total: 0.5; Total categorized by Sectors* VI: 1 |  | 1
Total |  |  |  |  | 6 | 2 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 4.4 | 1 | 0 | 5.4 | 6 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 7
* Projects should be categorized for following sectors
|  |  | Circular Code | Sector name | [16 empty] | Total: ** Physical progress
|  |  | I | Village Roads, Culverts, Bridges, Side Drinage etc. | [16 empty] | Total: A - Estimates are being / to be prepared/Identification Location/ Identification of needs/Call for Application
|  |  | II | Warehouses Facilities for Agricultural Production | [16 empty] | Total: B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared preparation of Project Reports & Estimates / Approval of the Project Reports & Estimates/Selection of Beneficiaries & Resource Person/ Call for Tender/ Evaluation of Tenders/ Awarding of Tenders/ Work program completed
|  |  | III | Economic Centers including Weekly Faires , Small Shops
|  |  | IV | Construction and renovation of Small Tanks ,Canals, Anicuts,Ponds and Agricultural Wells
|  |  | V | Community Drinking Water Supply Projects
|  |  | VI | Development/Modernization of Rural Health Centers and Providing Facilities | [16 empty] | Total: C - For Constructions : Start construction work,40% completed, Other : placed order for goods / Start of the program
|  |  | VII | Providing and Developing Electricity, Water and Sanitary Facilities for Schools | [16 empty] | Total: D - For Constructions : 60% completed Other : Received goods /instruments as per the order/ Start of the Training Program & Continuation/ Completion of Traning Program
|  |  | VIII | Projects for Prevention of Disasters for Human habitants from wild Animals | [16 empty] | Total: E - For Constructions 80% completed Other : Received goods /instruments as per the orderMoney payed in full & work not completed
|  |  | IX | Other Physical Infrastructure Improvement Projects Which are Directly Contibuted to Rural Economic Development | [16 empty] | Total: F - For Constructions 99% completed Other : Completed lists of goods and beneficiariesWork completed & payment nor completed